## Sheet1
Procurement List (Cells with Green color - Item Procured)
ReqID | Module | Supplier | No of units | Cost | Delivery Time | LINK | Comments
Req.024 | bq76920EVM: µC-Controlled AFE Family for 3s-5s-Series Cell Li-Ion and Phosphate Evaluation Module | Texas Instrument | 1 minumum | Digikey: 181.36 Euro Mouser: 198.17 | 2-4 days | Digikey_BQ76920 | Procured on 01.12.2022
Req.024 | DollaTek Battery BMS Board Module Li-Ion Li-Polymer Battery Pack Protective Board BMS for 13S 48V / 54.6V Batteries | AMAZON | 2 | 13 Euro | 1-2 Days | 13s BMS Amazon | Procured on 15.11.2022
Req.024 | 4Series 30A 14.8V BMS PCB Battery Protective Board with Balance Function for 18650 Li-Ion Lithium Battery Cell with Wire | AMAZON | 2 | 8 Euro | 1-2 Days | 4s BMS Amazon | Procured on 17.11.2022
Req.024 | Voltage Current Module, 0-36V 20A Current Sensor Module | AMAZON | 1 | 20 Euro | 1-2 Days | Current Sensor Module | Procured on 31.11.2022
| Dollatek MAX3232 RS232 Serial Port To TTL Converter Module DB9 Connector W/4 Jump Cables | AMAZON | 1 | 5.99 | 1-2 Days | https://www.amazon.de/Dollatek-MAX3232-RS232-Serial-Converter-Module-DB9-Connector/dp/B07DK3874B/ref=mp_s_a_1_4?adgrpid=71478802712&gclid=CjwKCAiA7IGcBhA8EiwAFfUDsVsBhJmVXYNikaWIw73IWTmVA1c7i1RY_pXUNAokg6iZij2jSWOJUxoCtRwQAvD_BwE&hvadid=597393993799&hvdev=m&hvlocphy=9117016&hvnetw=g&hvqmt=e&hvrand=6285348865195989745&hvtargid=kwd-296005655453&hydadcr=26570_2660021&keywords=rs232+ttl+konverter&qid=1669375227&sr=8-4
NA | XT60 connector | AMAZON | 1 | 8 Euro | 1-2 Days | XT60 connector | Procured on 30.11.22
Req.001 | Wacent Power Supply Module, Electronic Component, Durable Accessory, DC-DC 10-60V to 12-97V 1500W 30A Voltage Up Converter Boost CC CV | AMAZON | Minimum 1 | 39.29 Euro | 5 working day | https://www.amazon.de | Need to Procure
Req.002 | ANGEEK 300W 20A DC-DC Converter Module Step Down Voltage Module Constant Current Adjustable Buck Converter | AMAZON | Minimum 1 | 12.99 Euro | 5 working day | https://www.amazon.de | Need to Procure
Req.003 | AZDelivery LM2596S DC-DC Power Supply Adapter Step Down Module Compatible with Arduino Includes eBook | AMAZON | Minimum 1 | 3.99 Euro | 5 working day | https://www.amazon.de | Need to Procure
Req.004 | Swetup Schottky Diode 30 A 50 V Axial 30SQ050 for Solar Panel Parallel Reflow Protection Diodes Silicone Diodes Barrier High Voltage Diode Rectifier for Electronic Components Pack of 20 | AMAZON | Minimum 4 | 9.99 Euro(Pack of 20) | 5 working day | https://www.amazon.de | Need to Procure
Req.005 | AZDelivery ESP32 NodeMCU Module WLAN WiFi Dev Kit C Development Board with CP2102 (Successor Model to ESP8266) Compatible with Arduino and Includes E-Book | AMAZON | Minimum 1 | 9.99 Euro | 5 working day | https://www.amazon.de | Need to Procure
Req.006 | DC-DC 4-38V to 1.25-36V Voltage Adjustable Converter XL4015 Buck High Power Buck Converter 5A | AMAZON | 1 | €3.29 Euro | 1-2 Days | https://www.amazon.de | Need to Procure
Req.007 | Relay, JQC-3F(T73)-5VDC 5P Coil Voltage: DC 5V | AMAZON | 1*4 | €9.19 (5X) | MAx. 1 week | https://www.amazon.de | Need to Procure
Req.008 | Resistor, 100 Ohm | AMAZON | 2*4 | €6.49 (100 pcs. x) | 1 weeks | https://www.amazon.de | Need to Procure
Req.009 | Resistor,10K | AMAZON | 4*4 | €6.49 (100 pcs. x) | 1 weeks | https://www.amazon.de | Need to Procure
Req.010 | Resistor,1K | AMAZON | 1*4 | €6.49 (100 pcs. x) | 1 week | https://www.amazon.com | Need to Procure
Req.011 | LED, Red/Green... | AMAZON | 2*4 | €7.99 mixed kit 10 colours | 1 week | https://www.amazon.de | Need to Procure
Req.012 | Diode, 1N4007 | AMAZON | 1*4 | €6.50 (100pcs) | 1 weeks | https://www.amazon.de | Need to Procure
Req.013 | Transitor,transistor P channel MOSFET IRF9540 MOSFET | AMAZON | 2*4 | €4.99 Pack of 10 | 1 weeks | https://www.amazon.de | Need to Procure
Req.014 | Connector, 2pins/3 Pins 2.54 mm Pitch PCB Mount Screw Terminal Block | AMAZON | 1*4 3pin 6*4 2Pin | €9.99 100 Pieces 5 mm 2 Pin / 3 Pin | 1 weeks | https://www.amazon.de | Need to Procure
Req.015 | Diode, 1N4733A | AMAZON | 2*4 | €4.99 Pack of 100 | 1 week | https://www.amazon.de | Need to Procure
Req.016 | Transitor,BC547 Transistor | AMAZON | 3*4 | €5.70 20 Pcs. x | 1 weeks | https://www.amazon.de | Need to Procure
Req.017 | Heatsink, TO-220 Heatsink Aluminum Cooling Insulator Mounting Kit for MOSFET Transistor TO-220 | AMAZON | 2*4 | €7.99 | 1 weeks | https://www.amazon.de | Need to Procure
Req.022 | Dual MOSFET Switching Module 400W High-Power - 5 Pieces Trigger Switch Drive Module, DC 5V-36V 15A | AMAZON | 1 set(5 modules) | 9.99 Euro | 1-2 Days | PMC Link | Procured on 28.11.22
Req.025 | CC CV Step Down Module Adjustable DC 6-40V to 1.2-36V Voltage Regulator Down Converter Constant Current Power Supply Module | AMAZON | 1 | 9 Euro | 1-2 Days | Charger 0-60V | Need to Procure
Req.025 | DC 6.5-36V 24V Step Down to DC 1.2V-32V 12V Volt Transformer Reducer 4.5A 75W CC CV Power Supply Module | AMAZON | 1 | 15 Euro | 1-2 Days | 0-36V Charger | Need to Procure